## North Yorkshire Local Plan (003
Reference | Plan name | Plan Event | Plan Event | Entry date | Actual date | notes
Nyc-lp-commence | Nyc-local-plan-2026 | publish-notice-intention-commence | 2026-10-02 | 2026-06-16
Nyc-lp-scope-start | Nyc-local-plan-2026 | scoping-consultation-start | 2026-10-23 | 2026-06-16
Nyc-lp-scope-end | Nyc-local-plan-2026 | scoping-consultation-end | 2026-12-04 | 2026-06-16
Nyc-lp-gw1 | Nyc-local-plan-2026 | gateway-1-self-assessment | 2027-04-30 | 2026-06-16
Nyc-lp-content-start | Nyc-local-plan-2026 | plan-content-evidence-consultation-start | 2027-09-04 | 2026-06-16
Nyc-lp-content-end | Nyc-local-plan-2026 | plan-content-evidence-consultation-end | 2027-10-15 | 2026-06-16
Nyc-lp-gw2s | Nyc-local-plan-2026 | gateway-2-advice-sought | 2028-05-05 | 2026-06-16
Nyc-lp-gw2p | Nyc-local-plan-2026 | gateway-2-advice-published | 2028-06-30 | 2026-06-16
Nyc-lp-prop-start | Nyc-local-plan-2026 | proposed-plan-consultation-start | 2028-09-29 | 2026-06-16
Nyc-lp-prop-end | Nyc-local-plan-2026 | proposed-plan-consultation-end | 2028-11-24 | 2026-06-16
Nyc-lp-gw3s | Nyc-local-plan-2026 | gateway-3-advice-sought | 2029-02-16 | 2026-06-16
Nyc-lp-gw3p | Nyc-local-plan-2026 | gateway-3-advice-published | 2029-03-30 | 2026-06-16
Nyc-lp-exam-sub | Nyc-local-plan-2026 | examination-submitted | 2029-03-30 | 2026-06-16
Nyc-lp-exam-pub | Nyc-local-plan-2026 | examination-recommendations-published |  |  |  | Dependent on PINS
Nyc-lp-adopt | Nyc-local-plan-2026 | adopted | 2029-10-26
Nyc-lp-gw3-fas | Nyc-local-plan-2026 | gateway-3-further-advice-sought |  |  |  | Not required presently
Nyc-lp-gw3-rap | Nyc-local-plan-2026 | gateway-3-repeat-advice-published |  |  |  | Not required presently
Nyc-lp-mm-start | Nyc-local-plan-2026 | main-modification-consultation-start |  |  |  | Not required presently
Nyc-lp-mm-end | Nyc-local-plan-2026 | main-modification-consultation-end |  |  |  | Not required presently
Nyc-lp-exam-pauses | Nyc-local-plan-2026 | examination-pause-start |  |  |  | Not required presently
Nyc-lp-exam-pausee | Nyc-local-plan-2026 | examination-pause-end |  |  |  | Not required presently
Nyc-lp-acs | Nyc-local-plan-2026 | additional-consultation-start |  |  |  | Not required presently
Nyc-lp-ace | Nyc-local-plan-2026 | additional-consultation-end |  |  |  | Not required presently
Nyc-lp-withdrawn | Nyc-local-plan-2026 | withdrawn |  |  |  | Not required presently
Nyc-lp-revoke | Nyc-local-plan-2026 | revoked |  |  |  | Not required presently