## Start Here Dashboard
S278 Application Dashboard
Project Information |  | Project Contact
Site Name |  | Developer
Planning ref |  | Highway Consultant
Target Start Date |  | NYC Officer
Submission Progress Dashboard
Status | Count
Approved | 0
Under Review | 0
Outstanding | 0
Not Applicable | 0
Completion % | 0%
Pre Construction Progress Dashboard
Status | Count
Approved | 0
Under Review | 0
Outstanding | 0
Not Applicable | 0
Completion % | 0%
Streetworks Progress Dashboard
Status | Count
Approved | 0
Under Review | 0
Outstanding | 0
Not Applicable | 0
Completion % | 0%
Post Construction Progress Dashboard
Status | Count
Approved | 0
Under Review | 0
Outstanding | 0
Not Applicable | 0
Completion % | 0%

## S278 Tracker
S278 Submission Tracker | [6 empty] | Key | Approved / Received | Submitted / Under Review | Required / Outstanding | Not Applicable | Please review tabs at the bottom of the spreadsheet for further details.
General | S278 Application Request Form | Planning Permission Decision Notice / S106 Agreement obligations | CDM Letter confirming PD and Designer insurance | Land Registry and Written consultation with affected landowners (where applicable) | Location Plan and Site Extent Plan (relating to planning permission) | Existing Detail / Site Clearance | Proposed Statutory Undertakers Drawing | Land Drainage Consent (where applicable) | S278 Legal Agreement Plan | Stage 1/2 RSA Auditors CV and Brief Agreed with NYCC | Bill of Quantities / Tender Estimate
Key Notes
Detailed Design | General Arrangement Plan(s) (including surfacing and kerbing) | MfS or DMRB ( please note any deviation) | Swept Path Analysis | Junction/roundabout Deflection and Geometry (where applicable) | Traffic Signs and Road Markings | Horizontal and Vertical Alignment Plan(s) | Pavement Design and Details (standard highways details) | Street Lighting Plan(s) and Proposed Utilities | Earthworks Design / Cut & Fill / External Levels | Drainage Plan(s) / S104 Plan and S106 Connection Plan (where applicable) | Passenger Transport Facilities (where applicable)
Key Notes
Supporting Documents | Stage 1/2 Road Safety Audit & Designer Response | Traffic Signals Documents (where applicable) | Structures Documents (where applicable) | Collision Risk Assessment (if not agreed at planning) | Speed Check Data (if not provided at planning) | Accident and Associated Analysis (STATS 19) (if not provided at planning) | Walking, Cycling and Horse-Riding Assessment & Review (where applicable) | Traffic Regulation Order Application and Project Brief (temporary or permanent) documents | Landscaping and Arboricultural Plan(s) / Assessment and Tree Removal / RPA Plans | Geotechnical Investigation / Existing Cores | Cycle & Pedestrian Facilities (existing and proposed)
Key Notes
Pre-Construction | Stage 1 /2 RSA - Overseeing Organisation Response signed | LHA confirmation of Bond, Fees and Commuted Sums | Legal Instruction to draft agreement | Pre-Commencement Conditions discharged | Legal Agreement Signed | Pre-Start Meeting and Pre-Start Information | Detailed Programme of Works | Contractor Insurance / Streetworks accreditation | Risk Assessment and Method Statements | Construction Management Plan | Existing Highway Condition Survey
Key Notes
Streetworks / Licences | TRO or TTRO Signed and Sealed | Section 184 / Section 50 / S171 | Traffic Management Plan(s) - including traffic signal / bus stop | Advanced/ Early Streetworks Notice / Public Transport Notice / Lane Rental | 3 month notice | Advanced notice (signs) of works to the public / Letter Drop | Pre-Start Meeting Actions completed | 10 day notice | Works Start Notice | Inspection and Remedials | Closed Notice
Key Notes
Post Construction | Stage 3 Road Safety Audit | Stage 3 RSA - Overseeing Organisation Response received, agreed and signed | Pre-Maintenance / Defect Inspection and Remedials Complete | Drainage Certificate/ CCTV | Electric Test Certification and Inspection | Completion of Works Certificate / Enter Agreed Maintenance Period (Typically 12 months) | Pre-Adoption Inspection and Programme for completing the remedials | Stage 4 Road Safety Audit (where applicable) | Commuted Sums / S106 Obligations | Final Inspection and Inventory documents received (Asbuilts / Health & Safety File) | Issue Final Certificate
Key Notes
Notes

## #General
Application Request Form | All S278 Application requests shall be made using the Appendix A (1) - S278 Application Request Form and sent to Development.Control@northyorks.gov.uk .
Planning Permission Decision Notice | Copy of the Planning Permission Decision notice and associated conditions to include the approved planning drawings of the highway works. As part of the S278 Design Audit, we must review whether the works proposed and the methods of working are in accordance with the planning permission.
S106 Agreement / Obligations | Signed copy of the agreement to be sent for the file to ensure all off-site highways works are included within the S278 extents.
CDM Letter | A letter from the Developer (CDM Client) confirming who the Principal Designer is and that the Designer/Principal Designer undertaking the works has the appropriate skills, knowledge and experience to undertake their duties under CDM Regulations. This must be a letter from the Developer – a letter from the Principal Designer is not sufficient. Furthermore, written evidence must be provided that the Developer’s Designer for the S278 highway works has a minimum f professional indemnity insurance, with no limit on the number of claims.
Land Registry and Written consultation with affected landowners (where applicable) | Copied of Land Registry Titles, including plans. Where adjoining/nearby landowners or properties are directly affected by the proposed works then evidence of consultation will need to be supplied, especially where land is being dedicated. Including Public Right of Way consultation / diversions.
Location Plan / Site Extent Plan | 1/2500 OS based with 250m coverage either side of site. Site Extent plan showing the extent of the whole planning permission using a red line. This is not the same as the Land Plan for the Agreement.
Existing Detail / Site Clearance | This is a drawing showing the existing layout of the site and surrounding area including existing level information, existing road widths, landscaping, trees and hedges, signs, lines, street lighting, kerbing, surfacing to be removed etc.;
Statutory Undertakers Drawing | Existing and proposed diversion routes
Land Drainage Consent | Works affecting existing ditches or watercourse
S278 Legal Agreement Plan | In accordance with colour / shading detailed in Appendix A (1) - S278 Application Request Form
Road Safety Audit CV's and Brief Approved | The Developer must liaise with NYC’s Engineer to commission an independent Stage 2 Road Safety Audit in accordance with GG119, and in doing so, agree the appointment of a suitably qualified Auditor via the submission of appropriate CVs and then subsequently agree an Audit Brief with North Yorkshire Council acting in the capacity of Overseeing Organisation. NYC Traffic Engineering Team must be given the opportunity to tender for this work
Bill of Quantities / Tender Estimate | A breakdown of the costs to undertake the works including ancillary works and/or any works associated with the S278 scheme.

## #Detailed Design
General Arrangement Plan(s) (including surfacing and kerbing) | This drawing should indicate the scope and type of work to be carried out and shaded, annotated as per the S278 request form. GA drawings ensure the scope and scale of the works can be seen in context. Throughout the detailed design, reference should be made directly to NYC's Standard Detail Drawings ensuring that you also read the associated Notes for Guidance for the respective details to ensure that you are applying the detail/options correctly.
MfS or DMRB | Please see design standards for developer funded works and refer to the NYC ‘Movement and Place Matrix’
Swept Path Analysis | Swept path plots are to include as appropriate the following vehicles, emergency vehicles e.g. fire tender; refuse vehicles; operational vehicles such as tanker for pump stations and any other vehicles at the discretion of the Engineer. Vehicle tracking speeds MUST be annotated next to each vehicle manoeuvre. The tracking speed should be appropriate for the location, with a minimum tracking speed of 10mph. Drawings must clearly show the chassis and the wheel tracking.
Junction/roundabout Deflection and Geometry | Detailed drawings to be submitted where required.
Traffic Signs and Road Markings | Required if not included on GA. Provide sign and post schedules including TSRGD diagram numbers and include sign face sizes, x-heights/dimensions, mounting heights, details of posts, lighting arrangements etc.
Horizontal and Vertical Alignment Plan(s) (Long Sections) | Horizontal to include radii, lane widths & dimensions and visibility splays/sight lines. Street Lighting and arboriculture features to be shown on this plan. Vertical to include Long Sections with VA, transverse sections, vertical visibility sections, contour plots and existing ground profile.
Pavement Design and Details / Typical Construction details (Cross Sections) | Copies of North Yorkshire Councils Highways Standard Details are available in electronic format on request. Including typical cross sections with full constructional details as well as cross sections at reasonable intervals, (or as agreed with NYC) Sections to clearly show the limit of proposed adoption where the works will increase the extent of highway. To include coring plan and results, skid tests, tie-in details, thicknesses and specification of the layers. If any High Friction Special Surfacing is proposed, the details shall be included (either on the GA or pavement drawings. A thorough justification for its use must also be provided.
Street Lighting Plan(s) / Proposed Utilities | Proposals for the Street Lighting, including a specification, must be supplied directly to NYC Street Lighting, or supplied and passed on as part of the package detailing the scheme. NYC may have carried out the Street Lighting Design. Showing any existing and any proposed trees/planting. Many regulatory signs must be illuminated throughout the hours of darkness by internal or external lighting if they are sited within 50 m of a street lamp forming part of a system of street lighting where the speed limit is greater than 20 mph. Utilities to include proposed Diversions. All existing utility apparatus should be located and proven by trial holes to confirm location, route and depth etc. a Roads and Street Works Permit and a licence under Section 171 of the Highways Act 1980 will be required for trial holes
Earthwork Design / Cut & Fill / External Levels | Where required Include any earthwork construction details including calculations and specifications for any earthworks design.
Drainage Plan(s) / S104 Plan and S106 Connection Plan (where applicable) | Drawings required if not included on GA. To include gully positions and connections, pipe sizes, invert levels, cover levels, gradients, manhole and soakaway details & schedules, soakage/infiltration tests, hydrobrake, petrol interceptors, attenuation, connections to outfalls and any other SuDS features. Submissions should a also include drainage calculations, interaction with any existing highway or utility adopted system, SuDs and who has agreed to manage and maintain them, (do not assume this will be the Council), Drainage details to Outfall including relevant drainage agreements (S104), consent and permissions also required.
Passenger Transport Facilities | Where passenger transport facilities are affected then the passenger transport provider will need to be consulted. NYC Passenger Transport team should be consulted

## #Other Supporting Documents
Stage 1 / 2 Road Safety Audit and Designer Response | RSA undertaken taken by independent third party. Developer to provide response to any issues raised and amend the design accordingly before issuing to the LHA for review / agreed action.
Traffic Signals Documents | Signal drawings are to include both PDF’s and packaged DWG versions of each drawing. The information shown on a preliminary design signal/crossing drawing shall include LINSIG modelling and TR2500 Controller specification; traffic signal poles/heads, controller, maintenance vehicle hard standing, road markings and a staging diagram. The intervisibility zones and Sight Stopping Distances shall be shown on the drawing. Modelling documentation to be provided in both PDF and a copy of the software model. To be reviewed and approved by NYC Traffic Signals team
Structures Documents | All drawings to be provided in BOTH PDF and packaged DWG formats including calculations and “Approval In Principle” (AIP) documentation.. Structural details must be submitted to NYC Bridges and Structures Team for Technical Approval.
Collision Risk Assessment | This is a location plot of accidents over the previous five-year period together with their type for a radius of 250m from the edges of the proposed works. Furthermore, an analysis of the accidents stating trends that are addressed by the proposals or that could be exacerbated shall be identified. Typically contained with Transport Assessment / Statement
Speed Check Data | Measurement of 85%centile vehicle speed including evidence of weather (wet/dry) during the measurement period. Typically contained with Transport Assessment / Statement
Accident and Associated Analysis (STATS19) | This is a location plot of accidents over the previous five-year period together with their type for a radius of 250m from the edges of the proposed works. Furthermore, an analysis of the accidents stating trends that are addressed by the proposals or that could be exacerbated shall be identified. Typically contained with Transport Assessment / Statement
Walking, Cycling and Horse-Riding Assessment & Review | Refer to GG142
Traffic Regulation Order Application and Project Brief (temporary or permanent) documents | TRO/Notice Applications must be submitted for validation and distribution to the in-house team who will lead on the TRO and associated consultation work. Note - the costs of this will be invoiced outside of the S278 Agreement process. The developer, with the assistance of NYC’s Engineer, will complete a Project Brief for all permanent and temporary Traffic Order work that is duly forwarded to the Highways Area Office who will undertake such works. Timescales of 6-9months for permanent Traffic Regulation Order.
Temporary Traffic Regulation Orders (TTRO) | Example such as temporary road closure, speed reduction etc. Dealt with by Area offices / Streetworks
Landscaping and Arboricultural Plans / Assessments | If any highway trees or planting are affected by the proposals then an Arboriculture Report will be required along with protection methods to be undertaken during the Works. This includes any tress or planting adjacent to the Highway where the roots may be affected by the proposals
Geotechnical Investigation | Test data to support design assumptions, including location plan calculations and specifications for any earthworks design. Including Geotechnical Reports and Earthworks Design. Where works involve significant carriageway widening or as requested by NYC, Developers are required to undertake a soil survey to establish the soil and ground water sulphate content and pH values at various locations within the site and at the depths of the deepest sewers. A copy of the geotechnical report is to be submitted for consideration at the earliest opportunity. Concrete classes and types cannot be approved until this information is made available and work should not commence below ground level until such approval has been granted. Roads and Street Works Permit and a licence under Section 171 of the Highways Act 1980 will be required for trial holes.
Cycle & Pedestrian Facilities | If not covered by GA and Horizontal Alignment.

## #Pre-Construction
Stage 1/2 RSA Overseeing Organisation Response | Developer to ensure that Stage 1/2 Road Safety Audit has been signed off by Overseeing Organisation (NYC)
LHA confirmation of Bond, Fees and Commuted Sums | Developer to receive letter of no objection for agreed S278 scheme and associated detailed drawings. A further letter confirming the Bond / Fees / Commuted Sums will also be issued. Commuted sums may be applied to the scheme to ensure the future maintenance for any features that are non standard. Further information can be found in the Interim Guidance Note on Commuted Sums.
Legal Instruction | Agreement drafting and issue (this can take 2 to 3 months depending upon complexity and workloads.
Pre-Commencement Conditions Discharged | Developer to ensure that any off site highway conditions attached to the planning permission are discharged or at minimum highway consultation recommended for discharge
Legal Agreement Signed | No works on the highway are permitted until the agreement is signed and the area within the red line vested to the developer/ contractor.
Pre- Start Meeting | To be undertaken no later than 2 weeks before the start date
Detailed Programme of Works / Streetworks Notices | Detailed programme of works and start date to be submitted at or after the pre-start. See next tab for streetworks info.
Contractor Street works / Insurances | Certificates, Accreditations and Insurances to be sent and reviewed. Written evidence must be provided that the Developer’s Contractor undertaking the S278 highway works has a minimum of £10 million of public liability insurance, with no limit on the number of claims.
Risk Assessment / Method Statement | RAMS to be provided for the works
Construction Management Plan | Should be submitted as part of planning application or discharge of conditions.
Highway Condition Survey | The LHA will require photographs as oppose to one long video. We are aware that parts of this road are not in the best shape so it is best hence the reason for the condition requiring the survey to better understand who will be responsible for any repairs / reinstatement at the end of development. Please see below Do’s and Don’ts of highway condition survey: Dos  Include a location plan.  Include a site plan showing the location of where the photographs were taken on the public highway. Please include the site boundary shown as a red line. Multiple drawings may be necessary to show the plan for larger sites  Show the full width of the footway or carriageway in photos.  Show a maximum of 3 photos per page, preferably landscape.  Ensure each photo is numbered according to the key on the site plan and are shown in numerical order.  Ensure the condition survey follows a logical route.  Ensure the scope of the condition survey goes beyond the site’s immediate boundary where vehicle activity can reasonably be expected. Please consider vehicle routing and loading areas. Don'ts  Show individual kerb stones, gullies or individual defects. If there is a defect, make sure it is clearly shown within one of the photographs and note the damage under the photograph.  Include more than three photos on one page.  Include photographs on the site plan.  Include any photographs of private land (unless a temporary or permanent fixture on the land might have bearing on the condition of the highway).  Include photographs that are shaded, unfocused, poorly exposed/lit or where the condition on the public highway is not clear

## #Streetworks
TRO or TTRO Signed and Sealed | Typically require 6 weeks notice prior to TRO works to sign and seal order
Section 184 | Only where approved at the discretion of the Development Management Engineer S184 requires the construction of a new site access, or requires alternations to an existing site access in advance of the main works under a S278 or S38 Agreement
Section 50 | Any person or organisation who wishes to carry out works on a highway, will need to apply for a street works licence (Section 50 Licence). Section 50 only required where works to highway do not form part of the S278 works (sewer works) This requirement does not apply to anyone acting under a statutory right.
Section 171 | Required if wanting to undertake trial holes / small excavations / minor highway alterations. Allows for persons to temporarily deposit building materials or other items in a street, or to make a temporary excavation, as long as they have the consent of the relevant highway authority
Traffic Management Plan | To be submitted and approved by Streetworks
Advanced/ Early Streetworks Notice / Public Transport Notice | Advance warning of major S278 works (greater than 3months in advance) Evidence of formal notice having been given to public transport service operators where diversions or timetable changes are required (minimum notice of 8 weeks required). Lane rental charges may apply - https://www.northyorks.gov.uk/roads-parking-and-travel/roads-and-pavements/charging-companies-roadworks-lane-rental-scheme
3 month notice | Major Works (anything over 2 weeks) will require a major streetworks notification. Once submitted the Area office will approve or refuse the application depending on the works already booked on the network. Start date will be confirmed using the 10 day notice.
Advanced notice (signs) of works to the public | Roadworks advanced warning signs should displayed 2 weeks prior to the works commencing. Letter drop to residents directly impacted by the works should be distributed within this time frame
Pre-Start Meeting Actions | Any actions raised at pre-start meeting required to be completed before works start on site.
10 day notice | To be submitted once agreement is signed and sealed to confirm the road space booked
Works Start Notice | To submit 'in progress' notice to streetworks
Inspections / Remedials | Development Management Officer to regularly attend site and also complete a final inspection prior to the closed notice being submitted to streetworks. Any remedials should be undertaken as soon as possible whilst the temporary traffic management is in place.
Stage 3 Road Safety Audit | To be undertaken within 48 hours of the works being completed - ideally when the temporary traffic management is in place to ensure that works are safe prior to opening / closing the streetworks notice
Closed Notice | Closed Notice to be submitted to Streetworks once all works and remedials have been undertaken

## #Post-Construction
Stage 3 Road Safety Audit & Developer response | To be undertaken within 48 hours of the works being completed by an independent party - CVs and Brief must be approved before hand as per the Stage 1/2. Any issues raised must be rectified or responded to.
Stage 3 RSA - Overseeing Organisation Response received, agreed and signed | Overseeing Organisation Response and agreed actions completed prior to placing scheme on maintenance
Pre Maintenance Remedial Work Complete | Agreed Remedial works to be completed prior to the issuing of the Completion of works certificate
Drainage (S104) Certificate/ CCTV of highway drainage including gullies | Documents required prior to issuing of completion of works certificate.
Street lighting inspection and Electrical test certificates | Streetlighting to inspect any new or relocated streetlighting columns and provide remedials where appropriate prior to maintenance.
Completion of Works Certificate / Enter Agreed Maintenance Period (Typically 12 months) | Once the LHA are satisfied the scheme will be put onto a 12month maintenance period (this can be increased at the discretion of the LHA) The scheme will also be on a reduced bond.
Pre-Adoption Inspection and Programme for completing the remedials | Ideally arranged prior to the end of the maintenance agreement. Programme must be submitted to ensure remedials are timely.
Stage 4 Road Safety Audit (where applicable) | Stage 4 Road Safety Audit required 12 months post construction however not applicable for all schemes and is at the discretion of the LHA.
Commuted Sums / S106 Obligations | Where applicable all commuted sums associated with S278 scheme must be paid prior to the issuing of the final certificate.
Final Inspection and Completion of Works Inventory submitted | Updated Health & Safety File (including as-builts)
Issue Final Certificate | NYC will arrange for the Land Charges Register to be updated accordingly and will arrange for the adoption to be included upon the list of adopted streets and highways asset register. The Certificate of Maintenance will be issued at the conclusion of the Maintenance Period for the Works and only once all necessary remedial works and any outstanding fees have been paid.